## Sheet1
Phase | Task name | Description | Start date | Length | Author
1. Requrement Analysis | 1. Collect and analyze requirements | Find the traditional approach for the service, and current IS system for office rental services. Analyze their strengths and weaknesses | 2015-05-11 | 2 days | TienLX, QuocNVH, ThanhTT, TuanTL
| 2. Identify and clarify main functions. | Define main flows which system will build to adapt, and main functions for system. | 2015-05-13 | 2 days | TienLX, QuocNVH, ThanhTT, TuanTL
| 3. Create project management plan | Define the overview of the project Create project plan | 2015-05-15 | 3 days | TienLX, QuocNVH
2. Design | 1. Defined overall system design | Design basis system architecture design | 2015-05-18 | 2 days | TienLX
| 2. Create entity-relationship diagram | From the defined use cases, create the ERD for the system | 2015-05-20 | 2 days | TienLX, QuocNVH
| 3. Create logical database diagram | Define the logical database diagram based on ERD | 2015-05-21 | 2 days | ThanhTT, TuanTL
| 4. Create class diagrams and definition | Create the classes with attributes and functions, along with its definition | 2015-05-22 | 3 days | TienLX, QuocNVH, ThanhTT, TuanTL
| 5. Create interaction diagrams | Include sequences diagrams and activity diagrams | 2015-05-24 | 10 days | TienLX, QuocNVH, ThanhTT, TuanTL
| 6. Create interface design | Design the user interface for the system applications | 2015-05-24 | 3 days | TienLX, QuocNVH, ThanhTT, TuanTL
| 7. Define main algorithms | Analyze and define the required algorithms for the system | 2015-05-26 | 2 days | TienLX, QuocNVH, ThanhTT, TuanTL
3. Implement | 1. Design physical database | Define the physical database design on SQL Server, and create database dictionary | 2015-06-01 | 4 days | TienLX, QuocNVH, ThanhTT, TuanTL
| 2. Define base structure | Define the base structure for the program | 2015-06-05 | 2 days | TienLX
| 3. Coding admin functions | Include manage account | 2015-06-08 | 10 days | TuanTL
| 4. Coding manager functions | Include manage appoinment, repair/rental list and manage contract list | 2015-06-08 | 10 days | ThanhTT, QuocNVH
| 5. Coding staff functions | Include manage office | 2015-06-08 | 10 days | TienLX
6. Coding customer functions
| 6.1. Coding request office flow | Include search office, request office, request appointment | 2015-06-18 | 10 days | BE: QuocNVH
FE: TienLX
| 6.2. Coding contract signing flow | Include the assign flow for manager and view assigned flow for staff | 2015-06-18 | 10 days | QuocNVH, TienLX
| 6.3. Coding contract extend/cancel flow | Include request extend contract and cancel contract | 2015-07-13 | 5 days | QuocNVH, TuanTL
| 6.4. Coding request repair flow | Include request repair office for customers | 2015-07-13 | 7 days | ThanhTT, TienLX
| 7. Coding additional mobile app | Include view assigned job for staff, view assigned and update the repair job for staff | 2015-07-20 | 6 days | BE: QuocNVH, TuanTL FE: TienLX, ThanhTT
4. Testing | 1. Create test plan | Create the test plan document for the system | 2015-07-27 | 3 days | TienLX
| 2. Create unit testing | Create the test cases for each functions describe in the implementation |  |  | ThanhTT
| 2.1. For admin functions | Create test cases for functions in manage account | 2015-07-31 | 5 days | TienLX
| 2.2. For manager functions | Create test cases for functions in manage repair and contract | 2015-07-31 | 5 days | TuanTL
| 2.3. For staff functions | Create test cases for functions in manage office | 2015-07-31 | 5 days | ThanhTT
| 2.4. For customer functions | Create test cases for functions for customer | 2015-07-31 | 5 days | QuocNVH
| 2.5. For mobile app | Create test cases for functions for mobile app | 2015-07-31 | 5 days | TuanTL
| 3. Testing and fix bugs | Base on the test cases, test the functions and fix bugs | 2015-08-03 | 3 weeks | TienLX, QuocNVH, ThanhTT, TuanTL
| 4. System integration test | Test the overall of the system, measure the performance of the system | 2015-08-05 | 3 days | TienLX, QuocNVH, ThanhTT, TuanTL
5. Operation and Maintenance | 1. Create installation guide | Define the system requirement for the server and client. document installation guild | 2015-08-10 | 2 days | TienLX, QuocNVH
| 2. Create User guide | Define the user manual for operating the system | 2015-08-12 | 2 days | TienLX, QuocNVH, ThanhTT, TuanTL
| 3. Maintenance and fix bugs | Tracking the system and fix the remains bugs while installation | 2015-08-14 | 7 days | ThanhTT, TuanTL