## Sheet1
No. | Product Deliverables | Task | TienLX | QuocNVH | ThanhTT | TuanTL | Unit | Size
1 | Report1 - Introduction | Project Information | O
|  | Introduction |  | O
|  | Current Situation | O
|  | Problem Definition |  |  |  | O
Proposed Solution
|  | Feature functions |  |  | O
|  | Advantages and disadvantages | O | O | O | O
|  | Functional Requirements | O
|  | Role and Responsibility | O
2 | Report2- Software Project Management Plan | Problem Definition |  | O |  | O
Project organization
|  | Software Process Model |  | O
|  | Roles and Responsibilities | O
|  | Tools and Techniques | O
Project management plan
|  | Software development life cycle | O |  |  | O
|  | Phase Detail | O |  | O
|  | All Meeting Minutes |  | O | O
|  | Coding Convention |  | O
3 | Report 3- Software Requirement Specification | User Requirement Specification | O |  | O | O
System Requirement Specification
|  | External Interface Requirements |  |  | O
Functional Requirement
|  | <Guest>Overview Use Case |  |  | O
|  | <Customer>Overview Use Case |  | O | O
|  | <Staff> Overview Use Case | O
|  | <Admin> Overview Use Case |  |  |  | O
|  | <Manager> Overview Use Case | O | O |  | O
|  | <System>Overview Use Case | O | O
|  | Non-functional Requirement |  |  | O
|  | Conceptual Diagram | O
4 | Report 4- Software Design Description | Design Overview | O |  | O
|  | System Architectural Design |  | O
|  | Component Diagram | O
Detailed Description Explanation
Class Diagram
|  | Overview | O |  | O
|  | Entity package | O |  | O
|  | DAO package |  |  |  | O
|  | Service Package | O
|  | Controller Package |  |  |  | O
|  | Mobile Package | O
Interaction Diagram
|  | <Guest> Sequence Diagram |  |  | O
|  | <Customer> Sequence Diagram |  | O | O
|  | <Staff> Sequence Diagram | O
|  | <Admin> Sequence Diagram |  |  |  | O
|  | <Manager> Sequence Diagram | O | O |  | O
|  | <System> Sequence Diagram | O | O
User Interface Design
|  | Guest Interface Design | O | O | O
|  | Customer Interface Design | O | O | O
|  | Manager Interface Design | O | O | O | O
|  | Mobile Interface Design | O
Database Design
|  | Logical Diagram |  |  |  | O
|  | Data Dictionary |  | O
Algorithms
|  | Clustering data | O
|  | Matching data | O
5 | Report 5 - Software Implementation and Test Document | Setup Environment | O
Coding admin functions
|  | Login / Log out |  |  |  | O | 1 | 1
|  | Manage account |  |  |  | O | 3 | 1
Coding manager / staff / owner functions
|  | Manage contract |  | O |  |  | 2 | 4
|  | Manage appointment |  | O |  |  | 2 | 2
|  | Manage repair/rental |  |  | O |  | 4 | 2
|  | Manage office | O |  |  |  | 2 | 4
|  | Manage rental item |  |  | O |  | 2 | 1
|  | Manage amenity |  |  |  | O | 2 | 2
|  | Manage amenity group |  |  |  | O | 2 | 1
|  | Statistics |  |  |  | O | 2 | 3
|  | Calendar | O |  |  |  | 2 | 2
|  | Validation | O | O | O | O | 5 | 4
|  | Pagination | O |  |  |  | 3 | 1
|  | Change repair flow |  |  | O |  | 4 | 3
|  | Change create office flow | O |  |  |  | 1 | 2
|  | Print contract |  | O |  |  | 3 | 3
Customer functions
|  | Login / Register |  |  | O |  | 1 | 1
|  | Search office | O |  |  |  | 2 | 5
|  | View home page |  | O |  |  | 1 | 1
|  | View office detail |  |  | O |  | 1 | 2
|  | Request appointment | O |  |  |  | 1 | 1
|  | Manage contract |  |  | O |  | 2 | 3
|  | Manage repair/rental |  |  | O |  | 2 | 2
|  | Request repair |  |  | O |  | 1 | 2
|  | Request rental |  | O |  |  | 1 | 2
|  | Manage request office |  | O |  |  | 1 | 2
System functions
|  | Clustering office | O |  |  |  | 2 | 5
|  | Schedule |  | O |  |  | 3 | 5
|  | Suggest office |  | O |  |  | 2 | 4
|  | Suggest assign job | O |  |  |  | 2 | 4
|  | Delete outdated appointment |  | O |  |  | 2 | 3
|  | Handling conflict on job assign | O |  |  |  | 2 | 4
Mobile functions
|  | Coding front app | O |  |  |  | 2 | 1
|  | Coding mobile adapter | O |  |  |  | 1 | 2
|  | Coding backend | O |  |  |  | 2 | 2
|  | Introduction |  |  | O
|  | Database Relationship Diagram | O
Performance Measures
|  | Clustering Performance | O
|  | Matching Performance | O
Test Plan
|  | Features to be tested |  | O
|  | Features not to be tested |  |  | O
System Testing Test Case
|  | Overview |  |  | O
|  | Guest Test Case | O
|  | Customer Test Case |  | O | O
|  | Manager Test Case |  | O | O | O
|  | System | O | O
6 | Report 6 - Software User's Manual | Installation Guide
|  | Setting up environment at server side | O |  |  | O
|  | Deployment at server side | O |  |  | O
|  | Client side environment setting | O |  |  | O
User Guide
|  | Guide for customer |  | O | O | O
|  | Guide for manager on web application |  | O
|  | Guide for staff on mobile application | O
|  | Appendix |  |  |  | O
Notes
No. | Function Types | Function Point Size
1 | Insert, Delete, Update, Simple Search, Login, Register, simple function or simple query on one table | 1
2 | Computed functions or joined query | 2
3 | Complex functions or multiple subquery | 3
4 | Constraint process and data integrity | 4
5 | Functions with implementing algorithms | 5
Note on C2: phuong: Each row is a topic in project document. Do not have more than 15 rows in each product deliverable. Content in this template is used for reference only and it is vary in each project
Note on D2: phuong: Only one member in line, who has main repsonsibilty in this task
Note on C7: phuong: Use Indent for sub-tasks
Note on C8: phuong: Use Indent for sub-tasks
Note on C22: phuong: Use bold format for tasks which have sub-tasks
Note on C23: phuong: Use Indent for sub-tasks